## Slide 1
NoQx Launch Plan
Skip the queue. Pre-order. Pickup.
Path from code-ready to live in stores · 2026-05-22

## Slide 2
Where we are today
Code-ready, infrastructure live, store accounts pending
NoQx
DONE
✓ Production web app live at https://noqx.co.in
✓ Cloudflare proxy + SSL Full mode
✓ Supabase production schema + auth + RLS verified
✓ Both Android APKs build, sign, and run on device
✓ iOS Capacitor scaffold compile-checks pass
✓ All legal pages live (Privacy, Terms, Refund, Shipping, Contact)
✓ Email infrastructure operational (Resend + Cloudflare routing)
✓ Brand assets: logo, splash, all icon sizes generated
✓ Store-listing copy + data-safety answers prepared
✓ 19/19 production smoke tests passing
✓ Razorpay code integration complete (test mode active)
✓ Mobile keystores generated + backed up (OneDrive)
PENDING (operator action)
○ Apple Developer Program enrolment ($99/yr)
○ Google Play Console signup ($25 one-time)
○ Razorpay KYC + live keys deployment
○ Supabase Pro upgrade ($25/mo) for DB backups
○ App store listings created + screenshots captured
○ Real canteen seeded (placeholder still live)
○ GST registration decision + flag set
○ FSSAI license number displayed on canteen pages
○ Production APK flipped + uploaded to Internal track
○ iOS signing material (after Apple Dev approves)
○ TestFlight build + verification
○ Submit for App Review (Play + Apple)
NoQx Launch Plan · Prepared 2026-05-22
2 / 10

## Slide 3
14-day timeline
From sign-ups to live in both stores
NoQx
When | What | Detail | Cost
Day 0 (Today) | Open 4 accounts in parallel | Apple Dev + Play + Razorpay KYC + Supabase Pro | $124 + $25/mo
Day 1-2 | Wait | Apple Dev review (24-48h) | $0
Day 2-3 | iOS signing setup | Cert + Profile + ASC API key → 6 GitHub secrets → TestFlight build | $0
Day 3-7 | Wait + setup | Razorpay KYC reviewed (3-7d). Meanwhile build Play listings. | $0
Day 5-7 | Live keys + screenshots | Razorpay live deployed, ₹1 test order. Capture 6+4 screenshots. | ₹1 in fees
Day 7 | Production flip | Real canteen seeded. Capacitor flip to noqx.co.in. Production APKs built. | $0
Day 7-10 | Internal testing | Upload AAB to Play Internal, IPA to TestFlight. Invite operator + client. | $0
Day 10-12 | Submit for review | Play review (1-3d). Apple review (24-48h). | $0
Day 12-14 | Approved → live | Rollout 100% on both stores. Open the canteen. | 🟢 LIVE
Critical path is external review wait: Apple Dev 24-48h, Razorpay KYC 3-7 days, app store reviews 1-3 days each.
NoQx Launch Plan · Prepared 2026-05-22
3 / 10

## Slide 4
Upfront costs (one-time)
Pay these once to get to launch
NoQx
Service | Cost | Why
Apple Developer Program | $99/yr | Required for App Store + TestFlight
Google Play Console | $25 once | Required to publish on Play Store
Razorpay account | FREE | 2% transaction fee charged per payment
Supabase Pro (first month) | $25 | Database backups + larger DB quota
Resend Pro (first month) | $20 | 50k emails / month included
Railway Pro (already paying) | $20 | Hosting infrastructure
TOTAL DAY-1 OUT-OF-POCKET | $214 | $124 one-time + $90 first month subscriptions
After day 1, you've spent $214. Apple + Play don't repeat; Supabase + Resend + Railway are monthly.
NoQx Launch Plan · Prepared 2026-05-22
4 / 10

## Slide 5
Monthly costs at scale
What you'll pay each month as the app grows
NoQx
Daily active students | Railway | Supabase | Resend | Cloudflare | SMS | Total
1,000 DAU | $20 | $25 | $20 | $0 | $5 | $70/mo
5,000 DAU | $50 | $35 | $99 | $0 | $20 | $200/mo
15,000 DAU | $100 | $85 | $399 | $0 | $50 | $630/mo
15k w/ FCM push | $100 | $85 | $99 | $0 | $50 | $330/mo
50,000 DAU | $300 | $135 | Enterprise | $20 | $150 | $1,000+/mo
At 15k DAU: re-enable push notifications (FCM, currently disabled) to drop email volume by ~70% → saves ~$300/mo.
PLUS Razorpay 2% fee on every order. At 15k DAU × ₹80 avg order × 30 days = ₹36L gross/mo → ₹72k Razorpay fee.
All services are usage-based: you don't pay for capacity you don't use. Scale up only as you cross thresholds.
NoQx Launch Plan · Prepared 2026-05-22
5 / 10

## Slide 6
What we need from the client
Decisions + content to unblock submission
NoQx
DECISIONS
• Apple Developer enrolment type: Individual or Organization (DUNS required)
• Razorpay account: KYC documents ready (PAN, GSTIN, bank, director ID)
• GST registration status: registered yet? If yes, share GSTIN
• Cookie consent: not needed (DECIDED, see privacy policy §8)
• FSSAI license number for canteen pages
• Real first partner canteen: name, address, college, opening hours
• Payment terms with canteen partner (revenue share %)
CONTENT TO PROVIDE
• Real first canteen menu (items + prices + categories)
• Real canteen photos (3-5 per canteen for student-facing display)
• App Store "What's New" copy for v1.0
• Demo student credentials for App Store reviewer
• Privacy contact email + grievance officer name (DPDPA §10)
• Apple Developer account credentials (for signing material upload)
• Play Console account credentials (for AAB upload)
• Razorpay live API keys (after KYC approves)
NoQx Launch Plan · Prepared 2026-05-22
6 / 10

## Slide 7
What's complete on the engineering side
All code paths tested, documented, and ready
NoQx
✓ Web application
Live at noqx.co.in. 19/19 smoke tests pass. Cloudflare proxy active.
✓ Mobile builds
Both Android APKs build, sign, install. iOS scaffold compile-checks.
✓ Brand assets
NoQx logo (with glittering) regenerated across 38 sizes. Splash + feature graphic.
✓ Native role isolation
Student app hides canteen-login UI. Worker app hides student links.
✓ Email delivery
Resend wired + verified. Password reset OTP confirmed live.
✓ Email routing
Cloudflare → support/grievance/privacy@noqx.co.in → forwards verified.
✓ Payment integration
Razorpay test mode working. Live key flip is a 60-second change.
✓ Data safety / privacy
Privacy policy DPDPA-compliant. No third-party trackers. Audited.
✓ Operational runbooks
On-call, rollback, launch-day, FCM re-enable — all written.
✓ Smoke + verify scripts
smoke-test-prod (19 checks). verify-razorpay-flow (5 checks). launch-day-stats.
✓ Deep linking
Android App Links: noqx.co.in/dashboard/* opens directly in app.
✓ UI fixes verified
Worker header safe-area. Old-order invoice fallback. Worker logout routing.
NoQx Launch Plan · Prepared 2026-05-22
7 / 10

## Slide 8
Risks + mitigation
What could delay launch and how we handle it
NoQx
Risk | Likelihood | Mitigation
Apple Dev review stuck | Medium | Apple manual verification rarely takes >48h. Follow-up via dev portal support if delayed.
Razorpay KYC rejection | Low | Documents pre-checked. If rejected, re-submit with clearer scans — 24h re-review.
App Store rejection round 1 | Medium | Common: demo credentials missing, IAP confusion. Resubmit fixes in 24-48h.
Play Store rejection round 1 | Low | Data-safety form pre-prepared. Mostly accepted on first try.
Razorpay live test fails | Low | Test mode flow validated; live flow uses same code path. Rollback to test mode in 60 sec if needed.
Cloudflare DNS propagation | Already done | Zone live since 2026-05-20. No further action.
DB data loss before backups | HIGH → mitigated | Supabase Pro upgrade BLOCKS launch. Day-0 action item.
First-week traffic spike | Low (1 canteen) | Cloudflare absorbs at edge. Railway scales to 70% CPU before we'd notice.
FCM push not enabled | Accepted v1 | Users refresh app to see updates. Re-enable in v1.1 per FCM_REENABLEMENT.md.
NoQx Launch Plan · Prepared 2026-05-22
8 / 10

## Slide 9
Post-launch monitoring
First 30 days are critical
NoQx
DAILY (first 7 days)
• Run launch-day-stats script (orders, payments, signups)
• Check Razorpay dashboard for failed payments (target <5%)
• Check Resend dashboard for email bounce rate (target <2%)
• Review UptimeRobot for any downtime alerts
• Triage any customer support tickets <4h response
WEEKLY
• Review Railway usage (CPU, memory, egress trending)
• Review Supabase DB size + query performance
• Customer retention metric (DAU, WAU)
• Operational retro: any new edge cases? Update runbooks
• Plan v1.1 fixes based on production feedback
FIRST 30 DAYS: enable FCM push notifications (FCM_REENABLEMENT.md)
Cuts Resend email volume by ~70% (saves ~$300/mo at 15k DAU). Requires Firebase project + 7 implementation steps.
QUARTERLY
• Audit Cloudflare WAF rules · rotate keystore backup verification · review pricing-tier upgrade thresholds
NoQx Launch Plan · Prepared 2026-05-22
9 / 10

## Slide 10
Next 24 hours
These four sign-ups start all wait-clocks in parallel. Do them this morning.
1. Apple Developer
$99/yr
developer.apple.com/programs/enroll
⏱ 24-48h activation
2. Razorpay KYC
Free signup
dashboard.razorpay.com
⏱ 3-7 day review
3. Play Console
$25 one-time
play.google.com/console/signup
⏱ Same-day activation
4. Supabase Pro
$25/mo
supabase.com/dashboard
⏱ Immediate
Total this morning: $124 + 90 minutes of clicking. After that you're waiting on external reviews.
Detailed steps in docs/LAUNCH_CRITICAL_PATH.md